## project
Project Planner
| PLAN | PLAN
ACTIVITY | START | DURATION | Days
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64
Main Project | 1 | 64
First Prototype | 1 | 9 | bar: Days 1 to Days 9
Basic Database | 1 | 3 | bar: Days 1 to Days 3
Web portal login | 4 | 4 | bar: Days 4 to Days 7
iOS App Login | 4 | 4 | bar: Days 4 to Days 7
iOS App With Menus | 6 | 4 | bar: Days 6 to Days 9
Second Prototype | 9 | 20 | bar: Days 9 to Days 28
Database Handles Level Info | 10 | 9 | bar: Days 10 to Days 18
Web Portal Add Class | 13 | 10 | bar: Days 13 to Days 23
Web Portal Add Students | 13 | 10 | bar: Days 13 to Days 23
Web Portal Add Levels | 13 | 10 | bar: Days 13 to Days 23
Web Portal Add Questions | 15 | 13 | bar: Days 15 to Days 27
iOS App Menu Graphics | 16 | 13 | bar: Days 16 to Days 28
iOS App Playable Level | 16 | 13 | bar: Days 16 to Days 28
iOS Secuirty Requirements | 16 | 13 | bar: Days 16 to Days 28
Web Portal Security | 16 | 13 | bar: Days 16 to Days 28
Final Prototype | 29 | 64 | bar: Days 29 to Days 64
Complete Database | 29 | 12 | bar: Days 29 to Days 40
Complete iOS Gpaphics | 29 | 12 | bar: Days 29 to Days 40
Complete iOS Application | 35 | 13 | bar: Days 35 to Days 47
Complete Web Format | 35 | 13 | bar: Days 35 to Days 47
Complete Web Portal | 35 | 15 | bar: Days 35 to Days 49
Performance requirements | 38 | 15 | bar: Days 38 to Days 52
Test/Debug Web Portal | 38 | 27 | bar: Days 38 to Days 64
Test/Debug iOS App | 38 | 27 | bar: Days 38 to Days 64
Test/Debug DataBase | 38 | 27 | bar: Days 38 to Days 64